## Slide 1: Project Based Learning
Semester II
January - April 2026

## Slide 3: Project
The project must present
A functional prototype that incorporates hardware, or a hardware–software combination.
Purely software-based projects are not permitted

## Slide 4: Project
Project Groups
Same groups as activities in all lab sessions
Maximum Budget
Maximum Rs 3000/- per group ( Final cost sheet to be produced)

## Slide 5: Evaluation of Term II
PBL Lab
Graded Assignments: Graded assignments each of 15 marks
Total of 45 marks
Project : 150 marks, will be scaled down to 50 for Term II evaluation
  Review-1 (25)
  Review-2 (25)
  Final Presentation (50)
Week wise Evaluation - 50 Marks
* Independent Component - Not a part of Makerspace

## Slide 6: Project Theme
Broad areas :
Waste management
Smart City
Energy management
Healthcare
Water management
Agriculture
Smart Toys

## Slide 7: Project Schedule ( All Graded activities )
Identification of project within theme given ( Week 2)
Project Review I :
Literature Review, Final problem statement and Gantt Chart ( Week 5)
Project Review 2:
Design , Block Diagram, Partial Implementation / submission of requirements and tentative budget ( Week 9)
Final Presentation with Mechatronics Project / Model / Poster (Week 11,12 &13)
Final Project exhibition ( Week 14 )

## Slide 8: PBL Project – Tentative Week-wise Schedule
Week No. | Expected Task | Details
1 | Project Introduction | PBL project PPT, themes and evaluation details
2 | Selection of theme | To choose theme or broad area of project for group project
3 | Need Statement, Problem statement Timeline chart & Hardware requirements | To write problem statement for their project (Refer to activity 2 last semester for details) Gantt chart preparation & list of components required (Refer to activity 2 last semester for details) Share Review -1 PPT
4 | Review-1 (25 marks) | Review-1 to be conducted as per shared rubrics
5 | Review-1 (25 marks) | Review-1 to be conducted as per shared rubrics
6 | Review-1 (25 marks) | Review-1 to be conducted as per shared rubrics
7 | Conceptual Design / Block Diagram | Conceptual design and Block diagram of project to represents major components, their relationships and working
8 | Proposed working Finalization of hardware & cost | Detailed project execution as prototype To finalize the cost sheet based on final components
9 | Review-2 (25 marks) | Review- 2 to be conducted as per shared rubrics
10 | Follow up & project building & optimization | Incorporate the suggestions and recommendations and final project model ready
11 | Final Project Presentation & selection (50 marks) | Final project presentation to be conducted as per shared rubrics Selection of 1 or 2 projects for exhibition
12 | Final Project Presentation & selection (50 marks) | Final project presentation to be conducted as per shared rubrics Selection of 1 or 2 projects for exhibition
13 | Final Project Presentation & selection (50 marks) | Final project presentation to be conducted as per shared rubrics Selection of 1 or 2 projects for exhibition
14 | Project Exhibition | Exhibition of selected projects